DELTA CORP

Financial Summary — FY2025 & Q1 2026 Integration Budget

Document Date: February 5, 2026 | Prepared by: CFO Office | Confidential

# 1. FY2025 Financial Performance

| Metric | FY2024 Actual | FY2025 Actual | YoY Growth |
| --- | --- | --- | --- |
| Annual Recurring Revenue (ARR) | $168,000,000 | $210,000,000 | +25% |
| Total Revenue | $172,000,000 | $218,000,000 | +27% |
| Gross Profit | $129,000,000 | $163,500,000 | +27% |
| Gross Margin | 75% | 75% | Flat |
| Operating Expenses | $145,000,000 | $178,000,000 | +23% |
| EBITDA | $27,000,000 | $40,000,000 | +48% |
| Net Revenue Retention (NRR) | 112% | 118% | +6pp |
| Customer Count (Enterprise) | 148 | 187 | +26% |
| Average Contract Value (ACV) | $1,135,000 | $1,123,000 | -1% |

# 2. Beta Acquisition Financial Summary

| Item | Value |
| --- | --- |
| Acquisition Price | $185,000,000 |
| Beta ARR at Close | $43,000,000 |
| Revenue Multiple | 4.3x ARR |
| Beta Gross Margin | 68% |
| Deal Close Date | January 31, 2026 |
| Financing Structure | 70% cash, 30% Alpha stock |
| Integration Budget (12 months) | $8,500,000 |
| Expected Revenue Synergies (Yr 1) | $6,000,000 |
| Expected Cost Synergies (Yr 1) | $3,200,000 |

# 3. Integration Budget Allocation

| Workstream | Budget Allocated | Spent to Date | Remaining | Status |
| --- | --- | --- | --- | --- |
| Technology Integration | $2,800,000 | $180,000 | $2,620,000 | ON TRACK |
| People & HR | $1,200,000 | $95,000 | $1,105,000 | ON TRACK |
| Customer Success | $1,500,000 | $220,000 | $1,280,000 | AT RISK |
| Sales & GTM | $800,000 | $0 | $800,000 | NOT STARTED |
| Legal & Contracts | $600,000 | $410,000 | $190,000 | OVER PACE |
| Vendor Consolidation | $400,000 | $0 | $400,000 | NOT STARTED |
| Systems & IT | $700,000 | $85,000 | $615,000 | ON TRACK |
| Contingency Reserve | $500,000 | $0 | $500,000 | RESERVED |
| TOTAL | $8,500,000 | $990,000 | $7,510,000 |  |

# 4. Vendor Spend — Combined Entity (Projected)

| Vendor | Alpha Annual | Beta Annual | Combined | Savings Opportunity |
| --- | --- | --- | --- | --- |
| AWS | $2,400,000 | $780,000 | $3,180,000 | $320,000 if consolidated to single EDP |
| Salesforce / HubSpot | $612,000 | $96,000 | $708,000 | $150,000 if migrated to single CRM |
| Microsoft 365 | $204,000 | $48,000 | $252,000 | $0 — tenant merge only |
| Snowflake / Databricks | $480,000 | $240,000 | $720,000 | $180,000 if consolidated |
| Datadog / Grafana | $190,000 | $36,000 | $226,000 | $60,000 if merged |
| TOTAL | $3,886,000 | $1,200,000 | $5,086,000 | $710,000 potential savings |

Note: Vendor consolidation savings of $710,000 are achievable within 12 months post-close if the Vendor Consolidation workstream begins immediately. This workstream is currently NOT STARTED.

DELTA CORP — CONFIDENTIAL | Financial Summary | FY2025